## Cost estimate
Type | Subtype | Task | Est. duration in hrs | Effective duration
Administrative | Design | Scribbles | 6
Administrative | Design | Moqups | 12
Administrative | Testing | Writing Test-Concept | 10
Administrative | RE | Requirements Engineering (through the project) | 40
Administrative | Security | Writing security access documentation | 6
Administrative | Database | Creating a database schema | 12
Administrative | RE | Creating administrative documents | 8
Preparation - Design | Setup | Setting up design environement | 2
Preparation - Design | Design | Navigation | 4
Preparation - Design | Design | Search | 2
Preparation - Design | Design | Modal | 2
Preparation - Design | Design | E-Mail-Layout | 4
Preparation - Design | Design | Basic CSS | 6
Phase 1 - Design | Design | Permission - Page | 2
Phase 1 - Design | Design | Users - Page | 2
Phase 1 - Design | Design | Login - Page | 2
Phase 1 - Design | Design | Reset - Password Page | 2
Preparation - Development | Setup | Environement setup | 2.5
Preparation - Development | Setup | Setting up skeleton app | 4
Preparation - Development | Setup | Create global component | 8
Preparation - Development | Database | Setting up the database | 1.5
Phase 1 - Programming | Database | Create User schema | 0.75
Phase 1 - Programming | Database | Create Permission Schema | 0.5
Phase 1 - Programming | Database | Create Group Schema | 0.25
Phase 1 - Programming | Type-Definition | Create type definitions | 1.5
Phase 1 - Programming | CRUD | CRUD functionality Users | 7
Phase 1 - Programming | CRUD | CRUD functionality Permissions | 8
Phase 1 - Programming | Backend | Create API - Users / Permissions / Groups | 3
Phase 1 - Programming | CRUD | CRUD functionality view Groups | 2
Phase 1 - Programming | Testing | Writing Tests Phase 1 | 4
Phase 2 - Design | Design | Design Base Data Pages (7 Pages) | 4
Phase 2 - Programming | CRUD | CRUD functionality Base - Data | 8
Phase 2 - Programming | Type-Definition | Create type definitions | 2
Phase 2 - Programming | Testing | Writing Tests Phase 2 | 2
Phase 2 - Programming | Backend | Create API - Base Data | 3
Phase 2 - Programming | Import | Import Base Data | 6
Phase 3 - Design | Design | Excel-Import | 3
Phase 3 - Programming | Programming | Excel-Import functionality | 6
Phase 3 - Programming | Programming | Basic Job - Page Structure | 2
Phase 3 - Programming | Programming | Basic Service / Basic Controller | 2
Phase 3 - Programming | Testing | Unit-Tests | 4
Phase 3 - Programming | Programming | Excel-Calendar Import | 8
Phase 4 - Designing | Design | Extend / adjust Job - Page Design | 1
Phase 4 - Designing | Design | Design all Job - Pages | 6
Phase 4 - Designing | Design | Create the E-Mail Design for Job's | 2
Fixing DB Schema | Database | Finalize Job / Task Schema | 3
Fixing DB Schema | Database | Refactor current Database structure | 3
Phase 4 - Programming | Type-Definition | Writing schema and types | 5
Phase 4 - Programming | Services | Writing Services | 3
Phase 4 - Programming | Programming | Create Job Manualy | 6
Phase 4 - Programming | Programming | List Jobs page | 2
Phase 4 - Programming | Programming | Job question | 2
Phase 4 - Programming | Programming | Job Approval | 2
Phase 4 - Programming | Programming | Job Correction | 3
Phase 4 - Programming | Programming | Job E-Mail functionality | 3
Phase 4 - Programming | Programming | Job-State-Handeling | 6
Phase 4 - Programming | Programming | Permission Management | 8
Phase 4 - Programming | Programming | Writing Test | 4
Phase 5 - Design | Design | Design Budget / Statistics Pages | 5
Phase 5 - Design | Design | Design final version of search | 2
Phase 5 - Design | Design | Design user profile page | 2
Phase 5 - Programming | CRUD | CRUD functionality budget | 6
Phase 5 - Programming | Programming | Connect Budget to Users & Markets | 4
Phase 5 - Programming | Programming | Implementing search (respecting permissions) | 3
Phase 5 - Programming | Programming | Implementing user profile page | 2
Workflow - Alpha | Bugfixing | Bugfixing | 4
Workflow - Alpha | Reserve | Reserve | 8
Workflow - Alpha | Testing | Updating Unittests | 4
Workflow - Beta 1 | Bugfixing | Bugfixing | 4
Workflow - Beta 1 | Testing | Testing / Writing Unittests | 2
Workflow - Beta 1 | Feedback | React to feedback and make adjustments | 6
Workflow - Beta 2 | Bugfixing | Bugfixing | 4
Workflow - Beta 2 | Testing | Testing / Writing Unittests | 2
Workflow - Beta 2 | Feedback | React to feedback and make adjustments | 6
Release Candidate | Bugfixing | Bugfixing | 2
Release Candidate | Testing | Testing / Writing Unittests | 0.5
Release Candidate | Feedback | React to feedback and make adjustments | 2
Go Live | Communication | Communication | 3
Go Live | Database | Erasing not needed data | 2
Go Live | Backup | Setting up Backup | 4
Go Live | Backup | Setting up automatic reporting | 2

## Time
Month | Days | Hours
November | 15 | 120
December | 11 | 88
January | 17 | 136

## Sums
Type | Time
Administrative | 94
Preparation - Design | 20
Phase 1 - Design | 8
Preparation - Development | 16
Phase 1 - Programming | 27
Phase 2 - Design | 4
Phase 2 - Programming | 21
Phase 3 - Design | 3
Phase 3 - Programming | 22
Phase 4 - Designing | 9
Fixing DB Schema | 6
Phase 4 - Programming | 44
Phase 5 - Design | 9
Phase 5 - Programming | 15
Workflow - Alpha | 16
Workflow - Beta 1 | 12
Workflow - Beta 2 | 12
Release Candidate | 4.5
Go Live | 11
Sub-Types | Hours | Cost
Administrative | 94 | 12220
Preparation | 36 | 4680
Phase 1 | 35 | 4550
Phase 2 | 25 | 3250
Phase 3 | 25 | 3250
Phase 4 | 53 | 6890
Phase 5 | 24 | 3120
Workflow | 40 | 5200
Release & Go Live | 15.5 | 2015
Fixing DB Schema | 6 | 780

## Time Chart
Phase | November | December | January
Administrative
Preparation
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
Workflow
Release & Go Live
Fixing DB Schema
Partialy
Full